## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://freecrm.co.in/index.html
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Free CRM delivers cloud-based and as well as a full range of software and choice in how you want it - licensed, on-demand, private label, and custom services. In scope Functionality: A. Login Module 1. User should be able to Login to FreeCRM by entering valid credentials on Login Panel. B.Add a new company by entering required details i)Click on contacts and create New contacts by entering details. ii)Click on Deal tab and Create a new deal. iii)Click on Tasks tab and create new tasks iv)Veirfy on calender weather the created tasks are reflecting on calender page. Out of Scope Functionality: Load Testing and Security Testing on Leave Management System. Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Story
Issue type | Summary | Description
|  | Objective | Acceptance
Epic | Contact | This epic is related to the UI of contact and functionality of contact and to create a contact.
Story | Create New Contact | As a registered user I can create new contact of customer so that I will stay connected with customer or team. | User can create contact by clicking on New contact button.
In Create new contact page On the top there should be cancel and Save button.
In Create new contact page there should be First Name and Last Name, Middle Name(s), Company, Access, Tags, Email, Category, Status, Description, Social Channels, Time Zone, Address, Phone, Position, Department, Supervisor, Assistant, Referred By, Source, Do not Call, Do not Mail, Do not Text, Birthday, Identifier, image
First name and last name should be mandatory. It can be any chracter or digit.
Access can be private or public. For private account there should be text box to mention name who can see the profile. Note:It should dispay public by default
As I click on Company field it should Show the suggestions for entered Company, Tags, Assistant in dropdown.
For valid email there should be textbox to mention the type of email id(for e.g Personal, Buisiness) Note: Valid email should be display (tick mark) and invalid should be display (cross mark). Note:Any number of email id can be added.
For category field there should be dropdown list(e.g: Lead, Customer, Contact, Affiliate).
For status there should be drpdown list(e.g:New, Active, Inactive, on Hold, Terminated, Hot)
For social Channels there should be dropdown list for social media type (Twitter, Facebook, Linkedin, Tiktok, Instagram) and text box for entering link for profile Note :Any number of social channel can be added.
There should be dropdown list for Time Zone which contain continent/time zone region.
For address field should have text boxes for Street, City, State, Zip code, Country) Note:There should be dropdown list for Country. Note:User can enter any number of adress just by clicking on + sign beside the country.
For Phone field shoild have text boxes for country, number, type of number(e.g Home, work, etc). Note:Dropdown list for Country.
For supervisor there should be suggestion list for the enterd contact name Note: User can enter any supervisor as well.
For Assistant there should be suggestion list for the enterd contact name. Note: User can enter any assistent as well.
For Assistant there should be suggestion list for the enterd contact name. Note: User can enter any assistent as well by clicking on add .
For Reffered by there should be suggestion list for the enterd contact name. Note: User can enter any Reffered by as well by clicking on add .
For source field there should be dropdown list(e.g:Website, Google, Refferal, Facebook, Repeat customer).
On-Off button for Do not Call, Do not Text and Do not Email. Note:It should be off by default.
Birthday field have 3 text boxes each for Day , Month, Year. Note:Day field can be empty or any date from 1 to 31, but more than that will automatically enter 31. Note:Month should have drop down list from January to December or it can be empty. Note:Year can be empty or any valid year.
There should be option to upload the image from system.
After clicking on Cancel, I should redirect to main Contact page.
After clicking on save aall data should get save and contact details should be displayed.

## Test_Scenario
Story Name | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
Create new contact | TS_1 | COG_47 | To verify the new option. | UI | 1 | Verify to click the New button.
| TS_2 |  | To verify the Valid First name and Valid last name | Functional | 2 | 1.Check by entering only characters and digitfor first name and last name. 2.Check by keeping first name and last name blank.
| TS_3 |  | To Verify the Middle Name(s) | Functional | 1 | 1.Check by entering middle name
| TS_4 |  | To Verify company name | Functional | 1 | 1.Check if there is conatct created with same company or not ,If not add new company
| TS_5 |  | To verify the public & private Access button for the new contact . | Functional | 1 | 1.Check the access get change or not and by default it is public
| TS_6 |  | To Verify Tags | Functional | 2 | 1.Check if there is contact created with same tag or not ,If not add newtag 2.Check to verify more than one tag get entered.
| TS_7 |  | To verify the email id | Functional | 3 | 1.Check if there is tick sign to indicate valid email id and verify to get save. 2.Check if there is cross sign to indicate the wrong email id. 3.Checkt to verify add more than one email.
| TS_8 |  | To verify the category name | Functional | 1 | 1.Check to verify the select the value from dropdown
| TS_9 |  | To verify the status | Functional | 1 | 1. Check to verify the selected the value from the Status dropdown get entered .
| TS_10 |  | To veify the fields of social channels | Functional | 2 | 1 Check to verify the enetred social channel get saved. 2. Check by entering more than one social channel.
| TS_11 |  | To verify the Time zone | Functional | 1 | 1.Check to verify time zone get added.
| TS_12 |  | To verify the address fields | Functional | 2 | 1.Check by entering street, City, state,zipcode and select country . 2.Check to verify enter more than one address fields.
| TS_13 |  | To Verify the Phone | Functional | 3 | 1.Check 10 digit phoneNo get save 2.Check invalid phone no . Show the error message. 3..Check More than one phone no get added
| TS_14 |  | To verify the description | Functional | 1 | 1.Check description get saved.
| TS_15 |  | To Verify the position | Functional | 1 | 1.Check to verify enetred position get saved
| TS_16 |  | To Verify the Department | Functional | 1 | 1.Check to verify Department get entered.
| TS_17 |  | To Verify Supervisor | Functional | 1 | 1.Check if there is conatct created with same supervisor name or not ,If not add new company
| TS_18 |  | To Verify Assistant | Functional | 1 | 1.Check if there is conatct created with same assistent name or not ,If not add new company
| TS_19 |  | To Verify reffered by | Functional | 1 | 1.Check if there is conatct created with same reffred by name or not ,If not add new company
| TS_20 |  | To Verify the source | Functional | 1 | 1.Check to verify the source will be get entered.
| TS_21 |  | To verify Do not Call Do not Email,Do not Text On-Off button | Functional | 1 | 1.Check On-OFF button is working for Do not call,Do not Email,Do not Text
| TS_22 |  | To Verify Birthday | Functional | 2 | 1.Check to verify the birthday get enter 2.Check wheather any invalid birthday get added.
| TS_23 |  | To verify the image to be upload | Functional | 1 | 1.Check to verify image get uploaded.
| TS_24 |  | To verify Save option | Functional | 1 | 1.Check to verify the after clicking on save all data should get saved
| TS_25 |  | To Verify Cancel button | Functional | 1 | 1.Check to verify the cancel option is working.
34

## Test_Cases
Test Case Id | Story/Folder | Test Name | Objective | Precondition | Priority | Steps | Test Data | Expected Result | Actual Result
TC_01 | /New Contact | Verify the New option in contact page | To verify the new option. | 1.User should be logged in. 2.Contact page should be opened 3.There should be New button at top right | Normal | 1.Click on Contact option. 2.Click on the New |  | All required fileds (First Name and Last Name, Middle Name(s), Company, Access, Tags, Email, Category, Status, Description, Social Channels, Time Zone, Address, Phone, Position, Department, Supervisor, Assistant, Referred By, Source, Do not Call, Do not Mail, Do not Text, Birthday, Identifier, image) should be displayed to create contact. | New contact page opened with all required fields
TC_02 | /New Contact | Verify the Valid First Name and Last name | To verify the Valid First name and Valid last name | New Contact page should be opened. | High | 1.In the new contact page enter any characters for both first name and last name | Aishwarya, Jadhav | User should be able to enter the first name and last name. | Valid first name and last name successfully enterd.
TC_03 | [5 empty] | 1.In the new contact page enter any digit for first name and digit for last name. | Aish2, Jadh2 | User should be able to enter the first name and last name .
TC_04 | /New Contact | Verify the Invalid First Name and Last name | To verify the blank First name and last name . | New Contact page should be opened. | High | 1. In the New contact page click save without entering first name and last name |  | The field First name is required, The field last name is required should display. | Expected error messge is displayed
TC_05 | /New Contact | Verify the Middle Name(s) | To Verify the Middle Name(s) | New Contact page should be opened. | low | 1. In the New contact page enter middle name | Balasaheb | Middle Name Should get added. | Middle Name(s) is added.
TC_06 | /New Contact | Verify company field | To Verify company name | New Contact page should be opened. | Normal | 1. In the New contact page enter company name | Capgemini | It should show "No search found " initially and when there is no contact is added in same company and should add add new company name else should automatically populate the company name in filter. | No search found is displayed initially and while entering the company name it showed suggested company name.
TC_07 | /New Contact | Verify the Public and Private Access | To verify the public & private Access button for the new contact . | New Contact page should be opened. | Normal | 1. In the New conatct page with access field click on the button having value public |  | Contact profile should turned to private with active suggestion text box to allow the access to other entered contact. Or else by default it will be public and can change to public as well. | Public and private button are working properly.
TC_08 | /New Contact | Verify Tags field | To Verify Tags | New Contact page should be opened. | Normal | 1. In the New contact page enter tags | #Cap | It should show "No search found " initially and when there is no contact is added in same Tag and should add new tag else should automatically populate the tag name in filter. | No search found is displayed initially and while entering the company name it showed suggested company name.
TC_09 | /New Contact | Verify Add more than one Tag | Should able to add more than one tag. | In new page there should be tag field. | Normal | 1.Enter more than one tag | #buisiness | Should able to add more than one tag | More than one tag get added successfully.
TC_10 | /New Contact | Verify valid Email | To verify the valid email id | New Contact page should be opened. | High | 1.In new contact page enter valid email id | aishwarya29@ gmail.com | It should display tick sign and text box should allow to enter the type of email(e.g.Personal, Business) | It showed the tick sign for valid email, type of mail could added.
TC_11 | /New Contact | Verify Invalid Email | To verify the Invalid email id | New Contact page should be opened. | High | 1.In new contact page enter invalid email id | aish.com | It should show the cross sign and should not accept till the valid email entered. | It showed cross sign for invalid email.
TC_12 | /New Contact | Verify The add more than one email | To verify The add more than one email | In new contact page there should be placeholder for Email address and Type of Email id(E.g. Personal email) | Normal | 1. In new contact page click on + sign. 2.Enter Email | p123@gmail.com | More than one email should be saved. | More than one email get added successfully.
TC_13 | /New Contact | Verify the category | To verify the category name | In New contact page there should be a category dropdown >Lead >Customer >Contact > Affiliate | Normal | 1.In new contact page select any value from category dropdown | ​Customer | It should accept the required value. | Customer value get entered.
TC_14 | /New Contact | Verify the status | To verify the status | New Contact page should be opened. Below Dropdown list should be displayed. >New >Active >Inactive >on Hold >Terminated >Hot | Normal | 1.In new contact page select status from dropdown | Select Active | Should save status after saving contact. | Active value get entered.
TC_15 | /New Contact | Verify the social channels | To veify the fields of social channels | 1.New Contact page should be opened. 2.There should be dropdown list(Twitter, Facebook, Linkedin, Tiktok, Instagram) to select social media type and textbox to enter the link of same social media profile. | Normal | 1. In new contact page select social media type and link for that profile. | Twitter, @aishwarya | Social channel should be added after saving contact. | Social channel get entered.
TC_16 | /New Contact | Verify the add more than one social channels | To verify the add more than for social channels. | 1.In New contact page, There should be dropdown list(Twitter, Facebook, Linkedin, Tiktok, Instagram) to select social media type and textbox to enter the link of same social media profile. 2.There should be add option for social channels. | Normal | 1. In new contact page select + sign of social channels. 2.Enter social media type and link. | Linkedin, www,linkedin.com/aishwarya | More than one social channels should be added. | It added more than one social channel successfully.
TC_17 | /New Contact | Verify the Time zone | To verify the Time zone | In New contact page, there should be Time zone dropdown which contain all continent/Timezone region | Normal | 1.In new contact page select dropdown value of Time zone | Asia/Kolkata | Timezone should get added. | Time zone get added succesfully.
TC_18 | /New Contact | Verify the Address | To verify the address fields | In new contact page Adrees field should have placeholder for Street,City, state, zip codeand dropdown for country name | Normal | 1.In new contact page enter street, City, state,zipcode and select country as all fields are not manadatory. | Vasant valley, Pune , Maharshtra, 2201 ,India | All entered data should be saved. | Address field should get saved.
TC_19 | /New Contact | Verify the add more tha one Address field | To Verify the add more than one Address field | In new contact page Adrees field should have placeholder for Street,City, state, zip codeand dropdown for country name | Normal | 1. In new contact page select + sign for address 2.Enter street, city, state, zip code and select country name | Laminton, Mumbai, Maharashtra, 234, India | More than one address should get added. | It added more than one address succefully.
TC_20 | /New Contact | Verify the valid Phone | To Verify the valid Phone | In new contact page for phone field there should be drop down for country name , placeholder for phone And type(e.g Home,Work) | Normal | 1.In new contact page Select country, enter phone number and type | India, 9345678923, Work | Phone no. should accept any 10 digit number and save. | Valid phone no. get added.
|  | Verify the invalid Phone | To Verify the invalid Phone | In new contact page for phone field there should be drop down for country name , placeholder for phone And type(e.g Home,Work) | Normal | 1.In new contact page Select country, enter phone number and type | United state, +123y, Home | Phone no. should not accept the invalid phone no. and should display the error message. | It not showing the error message.
TC_21 | /New Contact | Verify the add more than one Phone | To verify the add more than one Phone. | In new contact page for phone field there should be drop down for country name , placeholder for phone And type(e.g Home,Work) | Normal | 1. In new contact page select + sign for phone. 2.Select country, enter phone number and type. | United States, +1(408)785-9962, Home | More than one phone no . Should get added. | More than one phone no. get added.
TC_22 | /New Contact | Verify the description. | To verify the description | New contact page should be opened. | Normal | 1.In new contact page enter the description | Small buisiness owner with 10 years experience in service environment solely responsible for all marketing communication, branding,PR, advertising search engine optimization activities. | Description should get added. | Description get added.
TC_23 | /New Contact | Verify the position | Verify the position | New contact page should be opened. | Normal | 1.In new contact page enter the position | Owner | Position should be added | Position added successfully.
TC_24 | /New Contact | Verify the Department | Verify the Department | New contact page should be opened. | Normal | 1.In new contact page enter the department | Marketing | department should be added. | department added successfully.
TC_25 | /New Contact | Verify Supervisor | To Verify Supervisor | New contact page should be opened. | Normal | 1. In the New contact page enter supervisor name | Aniket | It should show "No search found " initially and when there is no contact is added in same supervisor name and should add new supervisor name else should automatically populate the supervisor name in filter. | No search found is displayed initially and while entering the supervisor name it showed suggested supervisor name.
TC_26 | /New Contact | Verify Assistant | To Verify Assistant | New contact page should be opened. | Normal | In the New contact page enter assistant name | Snehal | It should show "No search found " initially and when there is no contact is added with same assistant name and should add new assistant else should automatically populate the assistant name in filter. | No search found is displayed initially and while entering the assistant name it showed suggested assistant name.
TC_27 | /New Contact | Verify reffered by | Verify reffered by | New contact page should be opened. | Normal | In the New contact page enter reffered by | Olivia | It should show "No search found " initially and when there is no contact is added with same referred by name and should add new referred by name else should automatically populate the referred by name in filter. | No search found is displayed initially and while entering the assistant name it showed suggested company name.
TC_28 | /New Contact | Verify the Source | Verify the source | In new contact page there should be dropdown for Source(Website, Google, Refferal, Facebook, Repeat customer) | Normal | In the New contact page select any source from dropdown list | website | Selected source should be saved. | Entered source get added.
TC_29 | /New Contact | Verify Do not Call Do not Email,Do not Text On-Off button | To verify Do not Call Do not Email,Do not Text On-Off button | In new contact page, the Do.not Call, Do not Email, Do not Text should be Off bydefault | Normal | In New contact page Click on Do not, Call Do not Email,Do not Text |  | ON value should get save | On-OFF button working properly.
TC_30 | /New Contact | Verify Valid Birthday | To Verify valid Birthday | In new contact page there should be text box for day and year and dropdown for month | Normal | 1.Enter any day 2.Select month dropdown 3.enter validyear | 1998-11-29 | Birthday should get save | Valid birthday get saved.
[6 empty] | 1.Enter day more than 31 | 35 | day field in Birthday will automatically saved as 31 only | It get update automatically to valid day for invalid day.
TC_31 | /New Contact | Verify invalid Birthday | To Verify invalid Birthday | In new contact page there should be text box for day and year and dropdown for month | Normal | In birthday field 1.Enter any valid 2.Select month dropdown 3.Enter invalid year | 13-Jan-30000 | Error messagge should displayed. | Its not showing the invalid year.
TC_32 | /New Contact | Verify Image | To verify the image to be upload | In new contact page there should be image upload option | Normal | 1.Click on upaod image option to upload image from system |  | Image should uploaded successfully. | Image added from system
TC_33 | /New Contact | Verify Save | To verify Save option | In new contact page There should be Save button at top | Normal | In New contact page Click on Save |  | All entered data should get save and should redirect to contact view page. | All data get saved.
TC_34 | /New Contact | Verify Cancel | To Verify Cancel button | In new contact page There should be cancel button at top | Normal | Click on Cancel |  | It should redirect to Contact main page without saving any data. | After clicking cancel it did not save any data and redirect to main contact page.

## Defect Report
Defect Id. | Defect Summary | Reported by | Date | Assigned To | Severity | Priority | Status | Module name | Build version | Reproducable | Reprosteps
COG_55 | In new contact page Phone field is not showing the error message for the invalid phone number | aishwarya.balasaheb-jadhav@capgemini.com | 2020-12-02 | abc@capgemini.com | High | High | To Do | Create New Contact | Sprint1 | yes | 1.In new contact page Select country, enter phone number and type
COG_56 | In new contact page Birthday field is not showing the error message for the invalid year. | aishwarya.balasaheb-jadhav@capgemini.com | 2020-12-02 | bcd@capgemini.com | High | Normal | To Do | Create New Contact | Sprint1 | yes | In birthday field 1.Enter any valid 2.Select month dropdown 3.Enter invalid year

## Test Summary Report
Test Summary Report for Sprint1 (27 - Nov to 02-Dec )
S.No. | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 10
2 | Created TestCases | 130
3 | No. of tests Executed in Sprint ,iteration 1 | 130 | 123 | 7
4 | Defects Reported | 6
5 | No. of Sprints Executed | 1
Any Challenges
Any Best Practises

## Burn Down Chart
Burndown chart

## Sprint Report
Sprint Report